## Sheet1
Name | Section | B.N | Tasks | Total Time | Problems Faced
Mahmoud Adas | 2 | 21 | cpu, io, ram, ram tests | 7 days | conflicts in signals when filling and flushing the decompressor buffer at same cycle, slow communication with the team to clarify the design.
Mohamed Shawky | 2 | 16 | solver (fixed step), interpolator integration and component test | 7 days | Main process design and integration, debugging through simulation and logs.
Remonda Talaat | 1 | 20 | interpolator components, solver memory IO | 5 days | components design and test.
Evram Youssef | 1 | 9 | solver (variable step), solver sub-procedures | 8 days | Solver became a huge file with a lot of conflicting signals.
Reham Gamal | 1 | 21 | fpu multiplication second algorithm + its tests, io testbench | 5 days | implementing multiplication algorithm twice as it's attached steps in first phase didn't work, i/o debugging
Mazen Amr | 2 | 8 | fpu adder, solver tests | 5 days | solver testing
Mohamed Ahmed Ibrahim | 2 | 9 | fpu multiplier first algorithm + its tests, interpolator tests | 5 days | using adder/subtractor components in the multiplier
Mahmoud Mohamed | 2 | 22 | fpu divider + its tests, solver tests | 5 days | using adder/subtractor components in the divider , solver testing